## Project Plan And Timeline Draft
Week (Sprint) | Dates | Phase Focus | Person A (AI / Data) Tasks | Person B (Cloud / UI) Tasks | Status
Week 1-2 | Apr 20 - May 1 | Phase 1: Data Foundations | Ingest PDFs, chunk data, tag metadata using Llama 3.2. | Source structured datasets, perform EDA, map taxonomy. | Planned
Week 3-4 | May 4 - May 15 | Phase 2: Database Infrastructure | Embed chunks and build the ChromaDB/Pinecone Vector DB. | Initialize PostgreSQL/MySQL; import clean structured data. | Planned
Week 5-6 | May 18 - May 29 | Phase 3: Retrieval & Core API | Build Hybrid Search logic; test Retrieval accuracy. | Build FastAPI skeleton; build endpoints for the Vector and SQL DBs. | Planned
Week 7-8 | Jun 1 - Jun 12 | Phase 4: The AI "Brain" & Matchmaker | Integrate Vision LLM; map out the LangGraph state machine. | Build telemetry logging; integrate the Recommendation scoring logic into the API. | Planned
Week 9-10 | Jun 15 - Jun 26 | Phase 5: Agent Tools & Frontend | Write Tool APIs (search DB, fetch doctors); refine system prompts. | Build Streamlit UI (chat state, file uploader, doctor recommendation cards). | Planned
Week 11-12 | Jun 29 - Jul 10 | Phase 6: Deployment & Handover | End-to-end edge-case testing; finalize model evaluation. | deploy to cloud host; finalize documentation. | Planned
DEADLINE | 2026-07-10 | Project Delivery | Final System Turn-In | Final System Turn-In | Milestone